## Projects
PROJECT TITLE: Student research projects
RESPONSIBLE: day-to-day work; ACCOUNTABLE: sign-off work; COUNSULTED: expert & specialist; Inform: stakeholders, keep in the loop
PROJECT START DATE |  | PROJECT END DATE |  | TODAY |  | CURRENT WEEK | DISPLAY WEEK
2025-11-01 |  | 2026-06-28 |  | 2026-04-23 |  | 24.7143 | 53
TASK ID | TASK TITLE | START DATE | DUE DATE | DURATION IN DAYS | WORK DAYS | Status | PCT OF TASK COMPLETE | 2026-10-26 | [6 empty] | 2026-11-02 | [6 empty] | 2026-11-09 | [6 empty] | 2026-11-16 | [6 empty] | 2026-11-23 | [6 empty] | 2026-11-30 | [6 empty] | 2026-12-07 | [6 empty] | 2026-12-14
 | time axis 2026-10-26 to 2026-12-20
 | time axis 2026-10-26 to 2026-12-20
STP1 | Project planning | 2025-11-01 | 2025-11-10 | 10 | 6 | Passed 164d | 100%
1 | Define project scope and objectives | 2025-11-01 | 2025-11-10 | 10 | 6 | Passed 164d | 100%
2 | Define research questions | 2025-11-01 | 2025-11-10 | 10 | 6 | Passed 164d | 100%
3 | Establish project timeline | 2025-11-01 | 2025-11-10 | 10 | 6 | Passed 164d | 100%
4 | Identify key milestones | 2025-11-01 | 2025-11-10 | 10 | 6 | Passed 164d | 100%
5 | Submit the project declaration | 2025-11-24 | 2025-11-24 | 1 | 1 | Passed 150d | 100%
STP2 | Literature review | 2025-11-11 | 2025-11-30 | 20 | 14 | Passed 144d | 100%
1 | Review BCI and EEG fundamentals | 2025-11-11 | 2025-11-30 | 20 | 14 | Passed 144d | 100%
2 | Review motor imagery calibration methods | 2025-11-11 | 2025-11-30 | 20 | 14 | Passed 144d | 100%
3 | Review gamification in learning and calibration | 2025-11-11 | 2025-11-30 | 20 | 14 | Passed 144d | 100%
4 | Review related EEG game systems | 2025-11-11 | 2025-11-30 | 20 | 14 | Passed 144d | 100%
5 | Review evaluation methods for user experience studies | 2025-11-11 | 2025-11-30 | 20 | 14 | Passed 144d | 100%
STP3 | Concept design | 2025-12-01 | 2025-12-07 | 7 | 5 | Passed 137d | 100%
1 | Define system overview and abstract architecture | 2025-12-01 | 2025-12-07 | 7 | 5 | Passed 137d | 100%
2 | Design high-level EEG-to-game data flow | 2025-12-01 | 2025-12-07 | 7 | 5 | Passed 137d | 100%
3 | Outline comparison framework for traditional vs BCG methods | 2025-12-01 | 2025-12-07 | 7 | 5 | Passed 137d | 100%
4 | Define key technical and research workflows | 2025-12-01 | 2025-12-07 | 7 | 5 | Passed 137d | 100%
STP4 | Interim Project Report | 2025-12-07 | 2025-12-08 | 2 | 1 | Passed 136d | 100%
1 | Submit the Interim Project Report | 2025-12-07 | 2025-12-08 | 2 | 1 | Passed 136d | 100%
STP5 | EEG device setup | 2026-02-23 | 2026-03-03 | 9 | 7 | Passed 51d | 100%
1 | Investigate suitable EEG device capabilities | 2026-02-23 | 2026-03-03 | 9 | 7 | Passed 51d | 100%
2 | Configure EPOC X environment and Cortex API access | 2026-02-23 | 2026-03-03 | 9 | 7 | Passed 51d | 100%
3 | Test device connectivity and EEG stream stability | 2026-02-23 | 2026-03-03 | 9 | 7 | Passed 51d | 100%
4 | Validate EEG-to-application pipeline feasibility | 2026-02-23 | 2026-03-03 | 9 | 7 | Passed 51d | 100%
STP6 | Interim Project Review | 2026-01-11 | 2026-01-12 | 2 | 1 | Passed 101d | 100%
1 | Submit the Interim Project Review | 2026-01-11 | 2026-01-12 | 2 | 1 | Passed 101d | 100%
STP7 | Dataset preparation and model training | 2026-03-18 | 2026-03-29 | 12 | 8 | Passed 25d | 100%
1 | Identify and select appropriate public MI datasets |  |  |  | - |  | 100%
2 | Design EEG preprocessing and signal cleaning pipeline |  |  |  | - |  | 100%
3 | Exploratory data analysis |  |  |  | - |  | 100%
4 | Train and compare candidate classification models |  |  |  | - |  | 100%
5 | Select final model for proof-of-concept deployment |  |  |  | - |  | 100%
STP8 | Game development | 2026-03-30 | 2026-04-13 | 15 | 11 | Passed 10d | 0%
1 | Develop game prototype |  |  |  | - |  | 0%
2 | Add calibration mechanics |  |  |  | - |  | 0%
3 | Design EEG-driven game controls |  |  |  | - |  | 0%
4 | Design game feedback and progression system |  |  |  | - |  | 0%
5 | Refine game usability and calibration user experience |  |  |  | - |  | 0%
STP9 | Final Progress Review | 2026-04-03 | 2026-04-06 | 4 | 2 | Passed 17d | 100%
1 | Progress summary |  |  |  | - |  | 100%
2 | Implementation state |  |  |  | - |  | 100%
3 | Analysis reflection |  |  |  | - |  | 100%
4 | Updated planning |  |  |  | - |  | 100%
STP10 | Realtime integration | 2026-04-13 | 2026-05-04 | 22 | 16 | In progress | 25%
1 | Build local realtime EEG prediction pipeline |  |  |  | - |  | 100%
2 | Create Python-to-GameMaker communication bridge |  |  |  | - |  | 0%
3 | Implement command streaming from model to game |  |  |  | - |  | 0%
4 | Test system latency, stability and command reliability |  |  |  | - |  | 0%
STP11 | Traditional method design | 2026-05-05 | 2026-05-10 | 6 | 4 | In 12 days | 100%
1 | Define traditional motor imagery calibration procedure |  |  |  | - |  | 100%
2 | Design cue-based left/right calibration task protocol |  |  |  | - |  | 100%
3 | Establish timing, instructions and logging standards |  |  |  | - |  | 100%
4 | Ensure fair structural comparability with BCG condition |  |  |  | - |  | 100%
STP12 | User study | 2026-05-11 | 2026-05-24 | 14 | 10 | In 18 days | 0%
1 | Design within-subjects comparative study protocol |  |  |  | - |  | 0%
2 | Prepare participant recruitment and experiment materials |  |  |  | - |  | 0%
3 | Plan data collection for both calibration conditions |  |  |  | - |  | 0%
4 | Define performance metrics and NASA-TLX implementation |  |  |  | - |  | 0%
5 | Experiment on participants |  |  |  | - |  | 0%
STP13 | Dissertation | 2026-05-25 | 2026-06-08 | 15 | 11 | In 32 days | 0%
1 | Report outline |  |  |  | - |  | 0%
2 | Finalize Introduction - Literature Review - Aims Objectives Scope |  |  |  | - |  | 0%
3 | Final project design methods |  |  |  | - |  | 0%
4 | Artefact design |  |  |  | - |  | 0%
5 | Implementation |  |  |  | - |  | 0%
6 | Experiement |  |  |  | - |  | 0%
7 | Experimental data analysis |  |  |  | - |  | 0%
8 | Discussion |  |  |  | - |  | 0%
9 | Conclusion, Limitations |  |  |  | - |  | 0%
10 | Edit, proofread and finalize submission document |  |  |  | - |  | 0%
STP14 | Poster | 2026-06-09 | 2026-06-15 | 7 | 5 | In 47 days | 0%
STP15 | Viva and Artefact Demonstration | 2026-06-16 | 2026-06-22 | 7 | 5 | In 54 days | 0%
1 | Develop artefact demonstration workflow |  |  |  | - |  | 0%
2 | Prepare viva presentation and key talking points |  |  |  | - |  | 0%
3 | Rehearse technical demo and Q&A responses |  |  |  | - |  | 0%
Formulas:
CURRENT WEEK = IF(OR([PROJECT END DATE]="",E8=""),"",IF(TODAY()>=[PROJECT END DATE],IF(TODAY()<=E8,"In progress","Passed "&TODAY()-E8&"d"),"In "&[PROJECT END DATE]-TODAY()&" days"))